## To Do
|  | Key Information About Event: |  | Date: March 25-27 2022 |  | Max 200 Scouts
If there is something that has to get done that isnt already in this document, ADD IT!!!
In the plan this year? | Catagory | Item to be done | Progress | Person Responsible | Expected Cost? | Time Frame | On What Step/Completed? | To Do List Items for Activity (1) | 2 | 3 | 4 | ...
Yes | Extremely Important | Making Flyer | Done | Tommy Rohmann | 0 | ASAP | 3 | Determine Disturbustion Method | Pick Flyer Format Accordingly | Make flyer based on date and activities | Proofread, export and distribute
Yes |  | Contact Chartwells | Confirmed/Must give check | Sladic |  |  |  | Emailed Henry 1/13/22
|  | Pier, ship, campus, fort, parking, | Confirmed/Need to update | Sladic |  |  |  | Keep School in Loop/Give Itinerary
Yes |  | School Permission (General) | Confirmed | Sladic |  |  |  | Keep School in Loop/Give Itinerary
Yes |  | Permission for Camping in Fort | Confirmed | Sladic |  |  |  | Keep School in Loop/Give Itinerary
Yes |  | Make Camporee Schedule | Inconfirmed/In Progress | Tommy Rohmann | 0 | ASAP |  | Outline Activities
Yes |  | Check Covid Protocols | Inconfirmed/In Progress |  |  |  |  | Chartwells requires Vaccine Card
Yes |  | Figure out Fraternity Availabilty | Inconfirmed/In Progress | Tommy Rohmann |  |  |  | Send email to see who is available to help host/run the camporee
|  | Remind/email list | IP | Jackson
|  | Website | IIP | Declan
Yes |  | Figure out Costs | Inconfirmed/In Progress | EVERYONE
Yes | Ship/Pier | Pier Access | Confirmed/Reach out | Sladic |  |  |  | Re-Contact Capt. begining of March
Yes |  | Turnout Gear | Confirmed/Reach out | Sladic |  |  |  | Mate G. said wouldn't be an issue
Yes |  | Fire Hose | Confirmed/Reach out | Sladic |  |  |  | Mate G. said wouldn't be an issue
Yes |  | Ship Tour | Confirmed/Reach out | Jackson/Sladic |  |  |  | Re-Contact Capt. begining of March
Yes | Simulators | Bridge Simulator | Confirmed/Reach out | Sladic |  |  |  | Spillane Confirmed access/Finalization will be closer to date
Yes |  | Engine Simulator/Lathe Demonstration | Denied | Jackson | 0 |  |  | Email sent 12/28/21
No | Products | T-Shirts | Na |  | NA
Yes |  | Patches | Inconfirmed/In Progress | Jackson | 2-3 apiece, approx 200 made |  |  | Design needs to be made, quote, and order places
Yes |  | Gift Bags | Inconfirmed/In Progress | Jackson | 0 |  |  | Admissions said yes, we just have to give them a number in Feb.
Yes | Campus Activities | Campus/Fort Tour | Inconfirmed/In Progress | Jackson | 0
Yes |  | Museum Tour | Inconfirmed/In Progress | Jackson
Yes | Other/Misc Activities | CG Drill | FT | Declan O
Yes |  | Morning Formation Stuff | Inconfirmed/In Progress
Yes |  | Admiral Visits Scouts | Inconfirmed/In Progress
Yes |  | Activity Competition Forms | Inconfirmed/In Progress | Tommy Rohmann
Yes |  |  | Inconfirmed/In Progress
Yes |  |  | Inconfirmed/In Progress
Yes |  | Getting Pictures from | Inconfirmed/In Progress
Stations
Rope
Sim
Ship tour
Tin foil boats
Coast guard drill
Turnout gear
Formation
Ice shackles